## Sheet1
Development Plan
Feature | Methods/Classes | Checklist items | Status | Date | Comments | Results/Changes
CHADS-VASc Calculator | Method: calculator | Answers using TTY-Prompt for user to select from | complete | 2019-09-03
|  | Install TTY-Prompt gem | complete | 2019-09-03
|  | calculate total score | complete | 2019-09-03
|  | write results to csv | complete | 2019-09-03
| method: evaluator | return stroke risk rating | complete | 2019-09-03
|  | use colorize gem to colour code risk rating | complete | 2019-09-03
|  | for moderate & high risk, ask if user wants to go to drug selector | will not implement | 2019-09-04 | suffice to return to main menu
View result | View result | open results csv for reading | complete | 2019-09-04
modify result |  | create a class to enable modification of result?? | will not implement | 2019-09-04 | not enough time, not a priority
Main app/menu |  | Selections: 1. CHADS-VASc calculator 2. View & modify results 3. Drug Selector 4. Patient med record |  |  | allow modify result only if have time
|  | option 1 - call calculator method | complete | 2019-09-04
|  | option 2 - call view result method | complete | 2019-09-04
|  | option 3 - call drug viewer method | complete | 2019-09-04 | allows viewing of a standard list of drugs
|  | option 4 - call med record method |  |  | grab patient name & score from previous entries & use to create instance object if possible