## Master Checklist
Software Implementation Plan
Feature | Methods/Classes/error types | Checklist items | Status | Date | Comments
CHADS-VASc Calculator | Method: calculator | Answers using TTY-Prompt for user to select from | complete | 2019-09-03
|  | Install TTY-Prompt gem | complete | 2019-09-03
|  | calculate total score | complete | 2019-09-03
|  | write results to csv | complete | 2019-09-03
| method: evaluator | return stroke risk rating based on cv score | complete | 2019-09-03
|  | use colorize gem to colour code risk rating | complete | 2019-09-03
|  | for moderate & high risk, ask if user wants to go to drug selector | not implemented
View result | View result | open results csv for reading | complete | 2019-09-04
modify result | Patient class | create a class to enable modification of result?? | partial |  | patient class created but feature not implemented
Main app/menu |  | Selections: 1. CHADS-VASc calculator 2. View & modify results 3. Drug Selector 4. Patient med record | deviated from initial plan |  | allow modify result only if have time. Drug selector is just a drug list view result only patient med record not implemented but add med function added
|  | option 1 - call calculator method | complete
|  | option 2 - call view result method | complete
|  | option 3 - call drug viewer method | complete
|  | option 4 - call med record method | complete | 2019-09-04 | grab patient name & score from previous entries & use to create instance object of a patient class if possible
add medication |  | load a list of medications that the user can choose from, then allow the user to select and add this medication to the patient's record | not implemented | 2019-09-03 | not enough time to implement
| ARGV | Use ARGV to enable adding a med outside of the program itself | not implemented |  | unable to make ARGV work with a class method. Have used a regular class method to enable adding medication for a patient
on-the-fly notes | ARGV | Use ARGV to add on-the-fly notes which will display face up to the user | complete | 2019-09-04 | displayed in table format
Error handling | Invalid selection from main menu | Handled in else statement to tell user that selection is invalid | complete | 2019-09-04
| CSV check for calculator method | Check that file exists. If it doesn't, warn user that results will not be saved and ask if want to continue | complete | 2019-09-05
| CSV check for view results method | Warn user that history doesn't exist and go back to main menu | partial | 2019-09-05 | if csv does not exist, rescue error message will display after user types in a name. Ideally want a different error message for this.
| Invalid name for view results | warn user that name doesn't exist in record | complete | 2019-09-05
| Invalid name for add medications | If patient does not exist in record | not started |  | currently rescue message displays at the end