## Sheet1
Development Plan
Feature | Methods/Classes/error types | Checklist items | Status | Date | Comments
CHADS-VASc Calculator | Method: calculator | Answers using TTY-Prompt for user to select from | complete | 2019-09-03
|  | Install TTY-Prompt gem | complete | 2019-09-03
|  | calculate total score | complete | 2019-09-03
|  | write results to csv | complete | 2019-09-03
| method: evaluator | return stroke risk rating | complete | 2019-09-03
|  | use colorize gem to colour code risk rating | complete | 2019-09-03
|  | for moderate & high risk, ask if user wants to go to drug selector | not implemented
View result | View result | open results csv for reading | complete | 2019-09-04
modify result |  | create a class to enable modification of result?? | partial |  | patient class created but feature not implemented
Main app/menu |  | Selections: 1. CHADS-VASc calculator 2. View & modify results 3. Drug Selector 4. Patient med record | deviated from initial plan |  | allow modify result only if have time. Drug selector is just a drug list view result only patient med record not implemented but add med function added
option 1 - call calculator method
option 2 - call view result method
option 3 - call drug viewer method
|  | option 4 - call med record method |  |  | grab patient name & score from previous entries & use to create instance object if possible
add medication | ARGV | Use ARGV to enable adding a med outside of the program itself |  |  | unable to make ARGV work with a class method. Have used a regular class method to enable adding medication for a patient
on-the-fly notes | ARGV | Use ARGV to add on-the-fly notes which will display face up to the user | complete | 2019-09-04 | displayed in table format
Error handling | Invalid selection from main menu | Handled in else statement to tell user that selection is invalid | complete | 2019-09-04
| CSV check for calculator method | Check that file exists. If it doesn't, warn user that results will not be saved and ask if want to continue | complete | 2019-09-05
| CSV check for view results method | Warn user that history doesn't exist and go back to main menu
| Invalid name for view results | warn user that name doesn't exist in record | complete | 2019-09-05